## Agent Flow
Background Agent - What It Does
Runs on a schedule (daily or weekly). Tools: get_values, get_table, compare_snapshots.
Step | Action | Detail
1 | Read data | Reads the latest market value data and league table from the data store.
2 | Compare snapshots | Compares with the previous snapshot to find notable changes: big value swings, or players whose value doesn't match their team's table position.
3 | Decide what to report | Agent uses its tools to decide which changes are worth reporting. This tool-calling and reasoning is what makes it agentic rather than a plain script.
4 | Write summary | Writes a short summary (e.g. 'Market movers this week') to the database, which the website displays.

## Azure Components
Azure Components
Piece | Service | Notes
Schedule trigger | Azure Functions (timer trigger) or Logic Apps | Starts the agent run on schedule.
Agent reasoning | Azure OpenAI or Azure AI Foundry (tool calling) | Check availability/quota on Free Trial early. Fallback: another model API behind the same Function.
Data | Cosmos DB or Azure Storage (tables/blobs) | Holds player values, table data and snapshots.
Website | Static Web Apps or App Service | Reads the agent summaries from the data store.
Secrets / identity | Managed identity + RBAC | No keys in code.
Observability | Log Analytics + KQL | Query tool calls and run results.

## Landing Zone Fit
How It Ties Into the Landing Zone
Landing zone control | How the agent workload uses it
RBAC (least privilege) | Function's managed identity gets minimal roles on the data store, and a read-only role for the AI service.
Private endpoints / VNet | AI service and data store use private endpoints inside the VNet.
Azure Policy | Tagging, region restriction and deny-public-access apply to every new resource.
Log Analytics + KQL | Demo query: which tools did the agent call in the last run, and did any fail?

## Build Order
Build Order (1-2 hrs/week)
Legend: yellow cells with blue text are yours to edit (Status, Hours done, Notes).
Example of expected format: | Status = In progress ¦ Hours done = 3.5 ¦ Notes = NSGs deployed, policy pending
Phase | Task | Status | Hours done | Notes
1 | Finish landing zone core (VNet, NSGs, RBAC, policy, monitoring) | Not started
2 | Deploy static site with a hardcoded dataset | Not started
3 | Move the data into Cosmos DB or Storage | Not started
4 | Add the Function and agent (last; optional if time runs short) | Not started
| Phases done | 0
| Progress | 0%
| Total hours done | 0